## Sheet1
At any time Company is waiting for customer to respond, the days for completing a task are extended by the same amout.
Make note of time for responses
Simplified |  |  | Days allowed | 0 | 3 | 10 |  |  | 10 | 15
Name | Address | size | fuel source | Application filed | Receipt of Application noted | Status of Completeness of application | Is application complete? | Screens passed (note which screens, if any, failed) | Initial Review completed | Total time | Witness Test scheduled | Agreement filed | Man-hours required | Notes (did applicant complete project, etc.)
|  |  |  | 2003-01-16 | 2003-01-19 | 2003-01-28 | Y |  | 2003-02-09 | 18
Expedited |  |  | Days allowed | 0 | 3 | 10 |  |  | 25 | 20 | 10 |  | 40/60 | Man-hours required
Name | Address | size | fuel source | Application filed | Receipt of Application noted | Status of Completeness of application | Is application complete? | Screens passed (note which screens, if any, failed) | Initial Review completed | Supplemental review, if necessary, completed | Agreement | Witness test scheduled | Total time | For Intial Review | For Supplemental Review | For Agreement |  | Notes (did applicant complete project, etc.)
|  |  |  | 2003-01-16 | 2003-01-19 | 2003-01-28 | Y
Days allowed
Standard |  |  |  | 0 | 3 | 10 |  |  | 20 | 55 | 30 |  | 15 | 125/150 | Man-hours required
Name | Address | size | fuel source | Application filed | Receipt of Application noted | Status of Completeness of application | Is application complete? |  | Standard Review completed | Impact Study, if needed | Facilities Study, if needed | Witness test scheduled | Agreement | Total time | For Impact Study | For Facility Study | For Agreement | Notes (did applicant complete project, etc.)
|  |  |  | 2003-01-16 | 2003-01-19 | 2003-01-28 | Y
Formulas:
Status of Completeness of application = [Application filed]+12
Initial Review completed = [Status of Completeness of application]+12

## Sheet2
DG Tracking Spreadsheet - MECo
Simplified | Expedited | Standard Review | Name | Joe's Meat Shop |  | Super Joe |  | Butcher Me Joe |  | Joe Meat |  | Joe's Meat Shop |  | Joe's Meat Shop
|  |  | Address | 26 Main St., Westboro, MA |  | 22 Main St., Westboro, MA |  | 24 Main St., Westboro, MA |  | 28 Main St., Westboro, MA |  | 26 Main St., Westboro, MA |  | 26 Main St., Westboro, MA
|  |  | ID number | M-1 |  | M-2 |  | M-3 |  | M-4
|  |  | size | 75 |  | 750 |  | 150 |  | 10 |  | 75 |  | 75
|  |  | fuel source | gas |  | gas |  | gas |  | gas |  | gas |  | gas
|  |  | DG type 1 | 1 |  | 2 |  | 1 |  | 5 |  |  |  | induction/cogen
|  |  |  | Date | Costs | Date | Costs | Date | Costs | Date | Costs | Date | Costs | Date | Costs
|  |  | Application filed | 2003-01-16 | 300 | 2003-01-16 | 2250 | 2003-01-16 | 450 | 2003-01-16 | 0 | 2003-01-16 | 300 | 2003-01-16 | 300
|  |  | Receipt of Application noted | 2003-01-16 |  | 2003-01-16 |  | 2003-01-16 |  | 2003-01-16 |  | 2003-01-16 |  | 2003-01-16
|  |  | Status of Completeness of application | 2003-01-21 |  | 2003-01-21 |  | 2003-01-21 |  | 2003-01-21 |  | 2003-01-21 |  | 2003-01-21
|  |  | Is application complete? | Y |  | Y |  | Y |  | Y |  | Y |  | Y
|  |  | Type of Review 2 | 2 |  | 3 |  | 6 |  | 1
Utility Service type3
|  |  | screen 1 | y
|  |  | screen 2 | y
|  |  | screen 3 | y
|  |  | screen 4 | n
|  |  | screen 5 | y
|  |  | screen 6 | y
|  |  | screen 7 | y
|  |  | screen 8 | y
|  |  | Initial Review completed | 2003-01-25
|  |  | Supplemental review, if necessary, agreed to by customer | 2003-01-25
|  |  | Supplemental review, if necessary, completed | 2003-01-26 | 1250 | [7 empty] | 1250 |  | 1250
Simplified |  |  | Agreement
Witness test scheduled
|  | Standard Review | Standard review completed (provide impact study estimate)
|  |  | Impact Study completed |  |  |  | 4500 | [5 empty] | 4500 |  | 4500
|  |  | Facilities Study completed |  |  |  | 4500 | [5 empty] | 4500 |  | 4500
SR Agreement completed
SR Witness test scheduled
For Initial Review
For Supplemental Review
For Impact Study
For Facilities Study
For Agreement
For Witness test
Includee a line for when the generator went online
What was the project's air quality status? (Reflect what's on the applicatoin
Did the project go to step 3 or 4 of ADR?
Were upgrades to the customer's Facility necessary?
Total business days and costs
Notes: Did project fail any screens? What was done in supplemental review? Cost of any system modifications? Reference where information is stored.
Indluce a line for when the generator went onlin
1) DG type: 1 - induction; 2 - synchronous; 3 - microturbine; 4 - fuel cell; 5 - solar; 6- wind; 7 - other. | [7 empty] | Include synchronous, induction, or inverter?
2) Type of review: 1 - Simplified; 2 - Expedited; 3 - Standard Review
3) Utility service type: 1 - radial; 2 - spot network; 3 - area network

## Sheet3
Notes Sheet
Name | Joe's Meat Shop
Address
ID number
Note | 0
Detail